## Table1 (hidden)
Column1
Pending
Ongoing
On Hold
Completed

## Remediations Isuues
Module | Tasks | Original Or Support | Priority | Status | % completion | Timelines | Comments
Payroll Module |  | Original | Medium Priority |  |  |  |  | Top priority
| Payslip design | Original | Medium Priority | Pending | 60%
| Emailing Payroll Slip | Original | Medium Priority | Pending | 0%
| P9 Report | Original | Medium Priority | Pending | 0%
HR Module
| Calc Fields for Employee Card: Leave details not updated. | Original | Medium Priority | Pending | 0%
| Auto Compute the leave balance | Original | Medium Priority | Pending | 0%
Review attendance and Leave balance report .

## Support Issues
NO | Subject | Department | Current Status | Closed Date
1 | Request for Review and Optimization of Attendance Report: Its too slow | ERP Support | Open
2 | Update timesheet to reflect holidays to allow proper leave posting with correct end date and return date. | ERP Support | Open
3 | Attendance report to reflect correct worked hours based on employee timesheet mapped | ERP Support | Open
4 | Automate attendance reports with UtimeMaster database. | ERP Support | Open
5 | Update leave reports for reporting purposes . | ERP Support | On Hold